## Corpus Plan
Corpus / Source | Category | Sub-category | Access | IP Owner | Ingest Method | Priority | Status | Total Sections Ingested | Total Words Ingested | Total Size in R2 | Total Size in Neon | % Ingested | Est. Sections | Est. Documents | Any issues | Notes
PRIMARY LEGISLATION | [7 empty] | 780171 |  |  |  | 0.76702 | 1017146
UK Primary Acts (~4,500) | Statute | Primary | Open | Crown / OGL | TNA CLML API | 1 | active | 160468 |  |  |  | 99.3% | 161574 | 4,500 |  | UKPGA back to 1267 (Statute of Marlborough). Split pre/post-2000 across 2 workers. AS OF 10 JUN: 2000+ done (90,838/90,860); pre-2000 at 98.5% (69,630/70,714) — ~1,084-section tail.
Statutory Instruments (~60,000) | Statute | Secondary | Open | Crown / OGL | TNA CLML API | 1 | complete | 235576 |  |  |  | 100.0% | 235572 | 60,000 |  | 3× section volume of Acts. Split pre/post-2010 across 2 workers. AS OF 10 JUN: si-2010plus 61,029 done; si-pre-2010 174,547/174,555. ~1,251 tail rows pending in queue.
Retained EU Law (~4,000) | Statute | Secondary | Open | Crown / OGL | TNA CLML API | 1 | stalled | 14390 |  |  |  | 10.3% | 140000 | 4,000 | Approved ~2h completion pass NOT yet run (CC action outstanding). True universe ~23k real sections; 140k denominator is phantom | EU-origin instruments now on legislation.gov.uk post-Brexit.
Scottish Acts + SSIs | Statute | Devolved Primary+Secondary | Open | Crown / OGL | TNA CLML API | 1 | active | 123621 |  |  |  | 77.3% | 160000 |  | Single "regional" corpus — not split by nation; figure is combined Scot+Wales+NI | Scottish Parliament legislation via legislation.gov.uk.
Welsh Acts + SIs | Statute | Devolved Primary+Secondary | Open | Crown / OGL | TNA CLML API | 1 | active | 123058 |  |  |  | see row 6 | 160000 |  | Counted within regional corpus (row above) | Senedd legislation.
NI Acts + Orders | Statute | Devolved Primary+Secondary | Open | Crown / OGL | TNA CLML API | 1 | active | 123058 |  |  |  | see row 6 | 160000 |  | Counted within regional corpus (row above) | Northern Ireland Assembly + Westminster Orders in Council.
Local / Private Acts | Statute | Primary | Open | Crown / OGL | TNA CLML API | 1 | Pending | [5 empty] | 10,000 |  |  | Lower priority – limited policy relevance.
TAX & FINANCIAL REGULATION
Tax Legislation (Finance Acts + tax SIs) | Statute | Tax | Open | Crown / OGL | TNA CLML API | 1 | Pending | [5 empty] | 120,000 |  |  | Subset of SIs. Included in SI worker allocation.
HMRC Technical Manuals (~80 manuals) | Administrative Guidance | Tax | Open | Crown / OGL | HMRC web scrape | 1 | active | 83203 |  |  |  | 83.8% | 640000 | 80 | hmrc-manuals: 16,061 rows done with no sections — classify (withdrawn/redirects?) | Already compiled. VATSAG, CTM, INTM, EIM etc. AS OF 11 JUN: manuals real universe measured at 85,197 (640k estimate was wrong); codes 14,067 + manuals 69,136 ingested.
FCA Handbook (COBS, MAR, SYSC etc.) | Statutory Guidance | Financial Regulation | Open | FCA (Crown body) | FCA Handbook API | 1 | complete | 3661 |  |  |  | 100.0% |  |  |  | FCA publishes structured handbook. Has a rudimentary API. AS OF 10 JUN: complete via discovered JSON API — 3,661 sections.
IBFD Tax Research Platform | Commentary | International Tax | Paywalled | IBFD (private) | Cannot ingest | 1 | Out of scope | [8 empty] | Private IP. Cannot reproduce even with subscription. Describe existence to Lex only.
REGULATORY & GUIDANCE BODIES
Sentencing Council Guidelines | Statutory Guidance | Criminal | Open | Sentencing Council / Crown | Web scrape (sentencingcouncil.gov.uk) | 2 | active | 253 |  |  |  | 12.7% |  |  |  | AS OF 10 JUN: unblocked, 253/~2,000.
College of Policing APP | Administrative Guidance | Criminal | Open | College of Policing | Web scrape | 2 | active | 1944 |  |  |  | 24.3% | 8000 |  |  | Authorised Professional Practice.
PACE Codes | Statutory Guidance | Criminal | Open | Crown / OGL | gov.uk direct download | 2 | Pending | [5 empty] | 800 |  |  | Small volume; bundle with Sentencing Council worker.
Civil Service / Ministerial Codes, Cabinet Manual | Administrative Guidance | Governance | Open | Crown / OGL | gov.uk direct download | 2 | Pending | [5 empty] | 500 |  |  | Cabinet Manual, Ministerial Code, Civil Service Code, Better Regulation Framework.
Treasury Green Book + Magenta Book | Administrative Guidance | Policy Methodology | Open | Crown / OGL | gov.uk direct download | 2 | Pending | [5 empty] | 500 |  |  | Cost-benefit and evaluation frameworks. Essential for costing module.
Erskine May + Parliamentary Standing Orders | Administrative Guidance | Parliamentary Procedure | Partial | Parliament | parliament.uk (partial open access) | 2 | Pending | [5 empty] | 3,000 |  |  | Erskine May now free online. Standing Orders open. Full historic volumes paywalled.
NHS Standard Contracts + NHSE Guidance | Administrative Guidance | Health | Open | Crown / OGL | NHSE web scrape | 2 | Pending | [5 empty] | 20,000
Planning Policy (NPPF, PPG) | Administrative Guidance | Planning | Open | Crown / OGL | gov.uk direct download | 2 | active | 791 |  |  |  | 15.8% | 5000 |  |  | National Planning Policy Framework + Planning Practice Guidance.
Building Regulations Approved Documents | Administrative Guidance | Building / Safety | Open | Crown / OGL | gov.uk direct download | 2 | active | 791 |  |  |  | 26.4% | 3000
CMA Guidelines + Merger Decisions | Administrative Guidance | Competition | Open | CMA / Crown | CMA website scrape | 2 | Pending | [5 empty] | 8,000
Ofcom / Ofwat / Ofgem / Ofsted Rules | Statutory Guidance | Regulation | Open | Crown bodies | Individual regulator APIs / scrape | 2 | Pending | [5 empty] | 40,000 |  |  | Each regulator has its own site; 4 separate scrapers needed.
Other Quango Rulebooks (~466 quangos) | Administrative Guidance | Regulation | Open | Crown / OGL | Web scrape (varied) | 2 | Pending | [5 empty] | 200,000 |  |  | Large long-tail. Automate discovery via gov.uk quango list.
LEGAL SCHOLARSHIP & COMMENTARY
HMRC Tax Information and Impact Notes (TIINs) | Explanatory | Tax Policy | Open | Crown / OGL | gov.uk scrape | 2 | complete | 791 |  |  |  | 100.0% | 800 | ~2,500 |  | Published for every Finance Bill measure since 2010. Plain English explanation of policy intent behind each tax provision. Distinct from HMRC manuals. AS OF 10 JUN: complete.
Office of Tax Simplification Reports | Commentary | Tax Policy | Open | Crown / OGL | gov.uk direct download | 2 | complete | 497 |  |  |  | 100.0% | 497 | ~50 |  | OTS abolished 2022 but all reports archived on gov.uk. Detailed analysis of specific tax areas (IHT, CGT, employment status). Explains what's broken and why.
Scottish Law Commission Reports | Commentary | Law Reform | Open | Crown / OGL | scotlawcom.gov.uk scrape | 2 | complete | 350 |  |  |  | 100.0% | 350 | ~200 |  | Scots law analysis and reform recommendations. Essential for devolved legislation. Separate from Law Commission (E&W) already in plan.
Northern Ireland Law Commission Reports | Commentary | Law Reform | Open | Crown / OGL | nilawcommission.gov.uk scrape | 2 | active | 17 |  |  |  | 34.0% |  | ~30 |  | NI-specific law reform analysis. Smaller volume but important for NI-specific legislation. AS OF 10 JUN: unblocked, 17/~50.
SSRN UK Legal Scholarship (free tier) | Commentary | Academic | Open | Authors / Open Access | SSRN API (api.ssrn.com) | 2 | blocked | [6 empty] | ~15,000 | Blocked — cause not yet investigated | Open-access legal scholarship on UK law. Papers on drafting history, policy intent, judicial interpretation. No rate limit on SSRN API. Abstracts free; full text varies.
PARLIAMENTARY RECORD
Hansard – Commons (1803–present) | Parliamentary | Debates | Open | Crown / Parliament / OGL | Parliament API (api.parliament.uk) | 3 | active | 6296891 |  |  |  | 98.3% | 2000000 | ~250,000 debates | 192 day-files failed (TWFY HTTP 503) — reset & rerun | Workers 1+2 join after Acts complete. Commons debates only. AS OF 11 JUN: per-speech migration complete — 6.30M sections.
Hansard – Lords (1803–present) | Parliamentary | Debates | Open | Crown / Parliament / OGL | Parliament API | 3 | active | 742876 |  |  |  | 87.1% | 500000 |  | 55 day-files failed (HTTP 503) — reset & rerun; % gap vs estimate likely denominator error | Workers 3+4 join after SIs complete. AS OF 11 JUN: per-speech — 742,876 sections. (+ Westminster Hall 237,135 [98.2%] tracked separately in Queue Snapshot.)
Bill Pages (text at each stage) | Parliamentary | Bills | Open | Crown / Parliament / OGL | Parliament API + bills.parliament.uk | 3 | Pending | [8 empty] | Full text, explanatory notes, impact assessments at each reading.
Committee Reports (Select + Public Bill) | Parliamentary | Committees | Open | Crown / Parliament / OGL | Parliament API | 3 | blocked | 0 |  |  |  | 0.0% |  | ~15,000 reports | Railway IP fails Cloudflare even with curl (V18 confirmed). New route: official Committees API (committees-api.parliament.uk) — research in progress | Pre/post-legislative scrutiny. Evidence sessions. Witness lists.
Parliamentary Written Answers | Parliamentary | Written Answers | Open | Crown / Parliament / OGL | Parliament API (api.parliament.uk) | 3 | active | 1391403 |  |  |  | ~62% | 1259593 | ~500,000 | 50 day-files failed (503/internal) — reset & rerun; denominators are era-average estimates, re-baseline after retry | Every written answer since 2000. Minister's own interpretation of legislation at point in time. Invaluable for "what does this provision mean in practice". AS OF 11 JUN: per-speech — wrans 1,219,784 + lordswrans 171,619.
Written Ministerial Statements | Parliamentary | Ministerial Statements | Open | Crown / Parliament / OGL | Parliament API (api.parliament.uk) | 3 | active | 44534 |  |  |  | exceeds est | 17487 | ~20,000 | Denominator (17,487) predates per-speech regrade — re-baseline | Formal statements made outside oral questions. Policy intent and interpretation direct from Ministers. AS OF 11 JUN: wms 23,676 + lordswms 20,729 + written-statements 129.
Explanatory Notes (Acts + SIs) | Explanatory | Parliamentary | Open | Crown / OGL | legislation.gov.uk API | 3 | Pending | [8 empty] | Plain English intent statements. Available since late 1990s.
Impact Assessments | Explanatory | Policy Evidence | Open | Crown / OGL | gov.uk / legislation.gov.uk | 3 | Pending | [8 empty] | Problem statement, counterfactuals, cost-benefit, intended outcomes. Gold for 'what were they solving'.
Post-Legislative Memoranda | Explanatory | Policy Evidence | Open | Crown / OGL | gov.uk scrape | 3 | Pending | [8 empty] | Patchy. 3–5 yr post-Act self-assessment. House of Commons Library tracks compliance.
White Papers + Green Papers (Command Papers) | Explanatory | Policy Evidence | Open | Crown / OGL | gov.uk + UK Parliamentary Papers | 3 | Pending | [8 empty] | Policy intent before legislation. Royal Commission reports included.
House of Commons Library Briefings | Explanatory | Policy Evidence | Open | Parliament / OGL | commonslibrary.parliament.uk | 3 | Pending | [8 empty] | Plain-English pre-Bill summaries. Exemplary research quality. Academic and stakeholder views.
The Public Whip (MP voting records) | Parliamentary | Voting | Open | Public Whip (charity) | publicwhip.org.uk API | 3 | Pending | [8 empty] | Tracks every division vote. 'Who pushed this through / who opposed it'.
PUBLIC CONSULTATIONS & EVIDENCE
Government Public Consultations + Responses | Policy Evidence | Consultation | Open | Crown / OGL | gov.uk Consultation hub API | 3 | Pending | [8 empty] | Consultation documents + response summaries. Shows what stakeholders said before legislation passed. gov.uk has a structured consultations listing.
ONS Statistical Datasets (cited in IAs) | Policy Evidence | Statistics | Open | ONS / Crown / OGL | ONS API (api.ons.gov.uk) | 3 | Pending | [8 empty] | Evidence base behind Impact Assessments. Metadata + headline figures rather than full datasets.
NAO Reports (post-implementation VFM) | Policy Evidence | Audit | Open | NAO / Crown | nao.org.uk scrape | 3 | blocked | 0 | [6 empty] | Client returns 0 sections — root cause not investigated | Post-implementation value-for-money assessments. 'Did it work and at what cost?'
CASE LAW
Find Case Law – TNA (2001–present) | Judicial | Case Law | Open | Crown / Open Justice Licence | TNA Find Case Law API (caselaw.nationalarchives.gov.uk) | 4 | active | 74874 |  |  |  | 99.8% | 75000 | ~50,000+ |  | Official source. Structured API. High Court, CoA, Supreme Court, Upper Tribunals. Open Justice Licence permits bulk reuse.
BAILII – full corpus (pre-2003 + tribunals) | Judicial | Case Law | Open | Crown / OGL (judgments); BAILII own copyright in HTML markup only | BAILII web scrape (polite, 1000ms floor) | 4 | blocked | 0 | [5 empty] | ~600,000 | Re-point planned: EAT/UT/FtT via Find Case Law + gov.uk ET decisions; BAILII contact found (Hale/Bell_West) — donation + access request; NI via judiciaryni.uk, Scotland via scotcourts.gov.uk | Separate organisation from TNA – independent IP rate limit. Text of judgments: Crown copyright / OGL. BAILII's HTML markup: BAILII copyright (we compile text, not markup). Covers: EAT back to 1970s, Privy Council, Scottish courts, NI courts, tribunals, ECHR cases.
Leading Cases – curated ~10,000 | Judicial | Case Law | Open | Crown / OGL | BAILII / TNA (subset) | 4 | Pending | [5 empty] | 50,000 | 10,000 |  | Priority subset for early Lex search quality. Use Gemini for richer case summary.
ECHR / ECtHR Judgments (HUDOC) | Judicial | International Case Law | Open | Council of Europe | HUDOC API (hudoc.echr.coe.int) | 4 | blocked | 0 | [6 empty] | HUDOC API endpoint changed Jun 2026 — /app/query/results returns 404; needs endpoint re-discovery | Separate source / separate IP / separate rate limit → own worker. UK courts must consider under HRA 1998.
Law Commission Reports | Judicial / Explanatory | Law Reform | Open | Law Commission / Crown | BAILII + lawcom.gov.uk | 4 | Pending | [8 empty] | Formal analysis of why current law is broken + reform recommendations. Already on BAILII.
INTERNATIONAL & COMPARATIVE
UK Treaties (FCO Treaties Online) | International | Treaties | Open | Crown / OGL | gov.uk FCO treaty database | 4 | blocked | 0 | [6 empty] | URLSearchParams fix applied but still 0 sections; needs queue reset + investigation | International obligations that constrain what UK legislation can do. Back to 1892.
EU Law – EUR-Lex (retained EU law origins) | International | EU Law | Open | EU Publications Office (open) | EUR-Lex API (eur-lex.europa.eu) | 4 | complete | 90260 |  |  |  | 100.0% | 232000 | 4,000 instruments |  | Source directives/regulations behind retained EU law. Separate source / separate rate limit. AS OF 10 JUN: eur-lex corpus complete — 90,260 sections.
OECD iLibrary – free summaries | International | Policy Commentary | Partial | OECD | OECD iLibrary (free tier) | 4 | complete | 505 |  |  |  | 101.0% | 500 |  |  | OECD Model Tax Convention commentary (full text paywalled). Free summaries and working papers ingestible. Full text requires negotiation / licence.
OECD Model Tax Convention Commentary | Commentary | International Tax | Paywalled | OECD (private publication) | Cannot bulk ingest | 4 | Out of scope | [8 empty] | OECD owns IP. Subscription gives read access only – no redistribution. Lex can reference existence and direct users to OECD iLibrary.
UN / UNCITRAL | International | International Law | Open | UN (open) | UNCITRAL website | 4 | Pending | [8 empty] | International trade law conventions. Lower priority for UK policy platform.
All UK International and multilateral treaties (ECHR, UNCLOS and about 15,000 others) | [5 empty] | 4 | blocked
COMMERCIAL / PAYWALLED – REFERENCE ONLY
Halsbury's Laws of England | Commentary | Legal Encyclopedia | Paywalled | LexisNexis (Reed Elsevier) – private IP | Cannot ingest | — | Out of scope | [8 empty] | Written by experts under commission. LexisNexis owns copyright in the commentary text itself (not just the platform). Subscription gives read access only. Even reproducing summaries at scale would require a licence. Lex can note 'Halsbury's covers this area' without reproducing content. Future: potential API partner / sponsorship route.
Westlaw UK headnotes + Key Number System | Commentary | Case Annotation | Paywalled | Thomson Reuters – private IP | Cannot ingest | — | Out of scope | [8 empty] | Thomson Reuters v ROSS (2025) confirmed headnotes are copyrightable editorial content. Underlying case text is Crown copyright / OGL and freely available via TNA. Only the annotations are paywalled. Future: potential API partner / sponsorship route — Scrutinise drives qualified traffic to their platform.
LexisNexis All England Law Reports | Commentary | Case Reports | Paywalled | LexisNexis – private IP | Cannot ingest | — | Out of scope | [8 empty] | Headnotes and editorial notes are LexisNexis IP. Raw judgment text is Crown copyright / free via BAILII/TNA. Future: potential API partner / sponsorship route.
HeinOnline Law Journal Library | Commentary | Academic Journals | Paywalled | William S. Hein (private) | Cannot ingest | — | Out of scope | [8 empty] | 3,200+ journals. Journal articles have dual copyright: journal publisher + author. Some older titles have open-access back-issues. Lex can cite article existence via CrossRef metadata.
IBFD International Tax Platform | Commentary | International Tax | Paywalled | IBFD (private) | Cannot ingest | — | Out of scope | [8 empty] | Private IP. No bulk access even with subscription.
Updated 11 Jun 2026 14:02 BST. Corpus total: 10,525,196 sections = 914,274 legacy (LegislationSection) + 9,610,922 new pipeline (corpus_sections). 83.7% of est ~12,571,298 (per-speech denominators). Neon: 9,178MB of 20GB. Queue: 0 pending ¦ 2,835 failed (2,538 committees + 297 pwdata 503s). | [6 empty] | Complete / Active / Pending / Blocked / Stalled / Out of Scope

## Queue Snapshot 11 Jun
Corpus | Ingested | Est. total | % | State
pwdata-debates | 6296891 | 6406800 | 98.3% | 192 failed (503) to reset
pwdata-wrans | 1219784 | 2003420 | 60.9% | 1 failed; gap likely estimate error — re-baseline
pwdata-lords | 742876 | 852984 | 87.1% | 55 failed (503) to reset
pwdata-westminster | 237135 | 241408 | 98.2% | complete bar tail
pwdata-lordswrans | 171619 | 249966 | 68.7% | 49 failed (503) to reset
pwdata-wms | 23676 | 26928 | 87.9%
pwdata-lordswms | 20729 | 22001 | 94.2%
primary-acts-2000plus | 90838 | 90860 | 100.0%
primary-acts-pre-2000 | 69630 | 70714 | 98.5% | tail — V19 audit
si-2010plus | 61111 | 61111 | 100.0% | complete
si-pre-2010 | 174547 | 174555 | 100.0%
eur-lex | 90260 | 90260 | 100.0% | complete
regional | 123641 | 160000 | 77.3% | V19 audit — discovery stopped short
tna-caselaw | 74874 | 75000 | 99.8%
hmrc-manuals | 69136 | 85197 | 81.1% | 16,061 done-rows wrote no sections — classify
hmrc-codes-guidance | 14067 | 14067 | 100.0% | complete
lda-commonsoralquestions | 69529 | 70000 | 99.3%
retained-eu | 14390 | ~23k real | 10.3% | approved completion pass outstanding
govuk-core-docs | 175 | 175 | 100.0% | complete
fca-handbook | 3661 | 3661 | 100.0% | complete
college-of-policing | 1944 | 8000 | 24.3% | V19 audit
building-regs / planning-policy | 1582 | 8000 | ~20% | V19 audit
sentencing-council | 253 | 2000 | 12.7% | V19 audit
written-statements | 129 | 17487 | 0.7% | V19 audit (overlaps pwdata-wms?)
nilawcom | 17 | 50 | 34.0% | V19 audit
committees-reports / evidence | 0 | 50753 | 0.0% | BLOCKED — CF on Railway; Committees API route in research
echr-hudoc / nao / uk-treaties / ssrn / bailii-* | 0 |  |  | BLOCKED — classification fetches pending (CCh)
TOTAL | 10525196 | 12571298 | 83.7% | #VALUE!

## Sources 10 Jun
Source (provider) | Access type used | Other access types available | Working? | Remaining workload | Why not producing / blocker | Action
TNA legislation.gov.uk | Bulk download + CLML XML | HTML, PDF fallback chain; research.legislation.gov.uk bulk (pre-release access granted) | YES | Small: acts/SI tails, regional 23%, local/private acts unseeded, explanatory notes unseeded, effects feed deferred | Nearly exhausted — this is success, not failure | Finish tails; seed local/private acts + explanatory notes when queue refilled
TNA Find Case Law | API | Bulk via API pagination | YES | ~270 sections (99.6% done) | — | Let it finish
TheyWorkForYou pwdata | Bulk XML download | — | YES | ~3M+ sections (debates, lords, wrans, wms, westminster) — THE largest available workload | Source works; historical backlog was never seeded. Queue starvation, not source failure | SEED THE BACKLOG — single highest-value action available
Parliament LDA API | API | — | YES | ~470 rows (oral questions tail) | — | Let it finish; written questions retired (covered by pwdata)
FCA Handbook | JSON API | HTML | DONE | 0 | — | —
HMRC gov.uk | HTML scrape | gov.uk bulk pages | YES | ~626k est (full-depth manuals never seeded) | Codes/TIINs complete; manuals seeding never run | Seed full-depth manuals
EUR-Lex | API | Bulk download service | DONE | 0 (90,260 done) | — | —
gov.uk direct downloads | Direct download | — | YES (method proven) | Small corpora: PACE, Green Book, codes, Cabinet Manual, white papers — all unseeded | Never seeded | Cheap wins — batch into one seeding sprint
committees.parliament.uk | HTML via curl | None viable from Node (CF TLS fingerprinting blocks Undici) | NO on Railway / PARTIAL local | ~10k reports + evidence | (1) curl not installed in Railway containers (2) Cloudflare 403s (3) residential IP works for reports-responses, rate-limited on other-publications | Install curl via nixpacks.toml; test Railway IP; fallback = local fetch on Charlie machine
ECHR HUDOC | API | HTML site | NO | ECtHR judgments | API endpoint changed Jun 2026 — /app/query/results returns 404 | CCh research task: find new endpoint (free, no CC needed)
NAO nao.org.uk | HTML scrape | PDF downloads | NO | VFM reports | Client returns 0 sections — never investigated | One CCh fetch test to classify the failure, then decide
UK Treaties (FCO) | API/HTML | gov.uk treaty database | NO | ~15k treaties | Still 0 sections after URLSearchParams fix — never investigated | Queue reset + one CCh fetch test
BAILII | HTML scrape | None (no API/bulk) | NO | ~600k pre-2003 + tribunal judgments | Cloudflare WAF; contact attempted, no reply | Chase contact; TNA covers 2001+ so gap is pre-2003 only — park
SSRN | API | — | NO | ~15k abstracts | Blocked — cause never recorded | One CCh fetch test to classify
Parliament Bills API | API | bills.parliament.uk HTML | NOT STARTED | Bill texts + explanatory notes | Never seeded | Horizon item (after pwdata)
Hansard API (historic) | API | — | NOT STARTED | Pre-TWFY-coverage debates | Never seeded | Horizon item